## Execution Plan (work places)
Work place | 0 | 1 | 2 | 3 | 4
House 2 |  |  | Michelangelo (1): tile
Room 2 |  | Bob (3): put walls | Michelangelo (1): tile
House 1 |  | Picasso (2): paint
Room 1 | Bob (3): put walls | Picasso (2): paint
Project 1

## Execution Plan (resources)
Resource | 0 | 1 | 2 | 3 | 4
Picasso |  | (2): paint (House 1, Room 1)
Picasso |  | (2): paint (House 1, Room 1)
Bob | (3): put walls (Room 1) | (3): put walls (Room 2)
Bob | (3): put walls (Room 1) | (3): put walls (Room 2)
Bob | (3): put walls (Room 1) | (3): put walls (Room 2)
Michelangelo |  |  | (1): tile (House 2, Room 2)

## Execution Plan (all actions)
Action | Input | Output | Start Time | End Time | Role | Resource | Capacity
finish shell construction | Project:1[init] | House:1[shell construction completed], Project:1[started] | 0 | 0 |  |  | 1
finish shell construction | Project:1[started] | House:2[shell construction completed] | 0 | 0 |  |  | 1
put walls | House:1[shell construction completed] | Room:1[walls put] | 0 | 1 | Builder | Bob | 3
paint | House:1[shell construction completed], Room:1[walls put] | House:1[painted], Room:1[painted] | 1 | 2 | Painter | Picasso | 2
put walls | House:2[shell construction completed] | Room:2[walls put] | 1 | 2 | Builder | Bob | 3
tile | House:2[shell construction completed], Room:2[walls put] | House:2[tiled], Room:2[tiled] | 2 | 4 | Tiler | Michelangelo | 1